Data management work flow

| Step | What Happens | Who is Responsible | Key Outputs / Deliverables |
| --- | --- | --- | --- |
| 1. Protocol & Study Design | Data requirements are defined; what endpoints, what variables are needed, how data will be collected, how often, etc. | Sponsor, protocol writers, statisticians, data management team | Final Protocol; CRF (draft) outline; Data Requirements Specification |
| 2. CRF / eCRF Design & Development | Based on protocol, CRFs are designed (questions, formats, validation rules). If electronic, build into EDC system. Ensuring usability, clarity, minimal burden. | Data managers, CRF designers, sometimes clinical operations, site input for feasibility | CRF/eCRF tools built; Validation rules defined; CRF annotations; Version control |
| 3. Database / System Setup | EDC / CDMS is configured. Access management, user rights, audit trails, security features. Also integration with other systems (labs, imaging, ePRO etc.) | Data management, IT, vendors | Validated database / system; SOPs for system usage; Integration interfaces; Test environment |
| 4. Data Management Plan & Validation Plan | Create detailed plan (who does what, when; timelines; definitions; data cleaning criteria; edit checks; safety reporting; deviations (enrollment, query); reconciliation processes) | Data manager, sponsor, sometimes CRO | Data Management Plan; Data Validation Plan; Edit check specifications; Access control documentation |
| 5. Site Training & Data Collection | Sites / investigators are trained on CRFs / eCRFs, data entry standards, handling of source documents. Then patient data begins to be collected. | Clinical operations, data management, site staff | Training materials; logs; initial data coming in; early data QC |
| 6. Data Entry / Capture / Data Monitoring | Data is entered / captured (electronic / paper). Validation checks run (automatically or manually). Queries / discrepancies are raised to sites. Ongoing monitoring of data quality. | Data managers, monitors, site staff | Cleaned data; query logs; correction of discrepancies; periodic data quality reports |
| 7. Data Cleaning / Reconciliation | Multiple sources reconciled (lab data, safety data, imaging etc.). Adverse events reviewed. Medical coding applied. Final reviews of missing data, outliers. | Data management, safety / pharmacovigilance, medical coding team, statistics | Reconciled datasets; coded data; clean data ready for analysis; issue resolution |
| 8. Freeze / Lock Database | Once cleaning is complete and all queries resolved, the database is locked so that no more changes can be made. | Data management + sponsor oversight + QA / QC | Locked database; audit trail; sign-offs; ready for statistical analysis |
| 9. Data Extraction / Transfer for Analysis | Data is extracted in required format(s), analysis datasets created, sometimes transformation or mapping into standards (e.g. SDTM, ADaM). | Data programmers / statistical programming teams | Analysis datasets; tables, listings, figures (TLFs); deliverables as per protocol |
| 10. Archiving & Documentation | All datasets, documentation (DMPs, CRFs, SOPs, audit logs) are archived. TMF (or eTMF) is completed. Ensuring regulatory readiness for inspections. | Data management, clinical operations, QA | Archived data and documents; clean TMF / eTMF; final reports; regulatory submission packages |

Practical / Real-World Considerations & Challenges

- Changing Requirements: Protocol amendments lead to CRF changes, new variables, which have knock-on effects. Managing version control is crucial.

- Data Quality vs Speed Trade-offs: Under pressure to meet deadlines, some teams may under-prioritize thorough cleaning, which risks downstream problems.

- Multiple Systems / Integration Issues: Lab systems, imaging, ePRO, external vendors — integrating data from different sources is error prone. Data mapping is needed; need to ensure format compatibility.

- Discrepancy / Query Backlog: Queries from sites can pile up, delaying cleaning; need clear workflows for raising, tracking, resolving queries.

- Regulatory & Compliance Requirements: Audit trails, validation of systems, data privacy, GCP compliance — teams must ensure documentation and system behavior satisfy regulators.

- Resource Constraints: Both in terms of staffing and budget; in smaller trials or academic settings, there may be limited resources for expensive or very robust EDC/CDMS systems.

- Training / SOP Compliance: Ensuring all site staff and data entry staff are trained and follow SOPs; inconsistencies in interpretation of data definitions or CRF instructions can cause data issues.

- Timeliness of Data Clean-up: Often data cleaning lags behind collection; delaying database lock; delaying analysis.

- Standardization: Using standard terminologies, data formats (e.g. CDISC) helps especially in multi-site / global trials, or when data needs to be shared or submitted to regulatory bodies.

Best Practices & Strategies That Help

- Good upfront planning: Strong protocol design, defining data to collect, variables, frequency, endpoints; early involvement of data management, statistics, clinical operations.

- Early CRF / database testing: Pilot CRFs, test edit checks, simulate workflows, sometimes mock data collection to identify issues.

- Automated validation / edit checks: E.g. built-in rules in EDC that catch inconsistencies (e.g. date of birth after visit date; ranges etc.).

- Centralized data flow & issue management: Having real-time dashboards, centralized query tracking, shared visibility so duplicates / conflicts are reduced. Encouraging collaborative review so data managers, site monitors, and others can see data quality status.

- Standardization: Use standards like CDISC for data submission, standardized medical dictionaries for coding, consistent definitions for endpoints and protocol deviations.

- Frequent QC / data cleaning cycles: Not waiting until the end — periodic clean-ups, interim checks.

- Robust documentation and audit trails: For every change / edit / query, there should be traceability. Also SOPs, system validation and user training.

- Risk-based approach: Prioritizing critical data fields and endpoints, focusing efforts on the highest risk items (the ones that could most affect study outcome).

Phase III CDM Workflow: Step-by-Step

| Phase | Key Activities | Who’s Involved | Deliverables / Checkpoints |
| --- | --- | --- | --- |
| I. Start-up / Setup | 1. Protocol finalization & review — Sponsor + regulatory / safety input; define endpoints, visit schedule, inclusion/exclusion, data sources. 2. Data Management Plan (DMP) written: roles, responsibilities, timelines, data standards (e.g. CDISC), medical coding, SAE/SAE reconciliation, data flow, vendor/data transfer specs. 3. CRF / eCRF design: design of case report forms (paper or electronic), mapping to protocol, specifying edit checks, derivations. 4. Database/CDMS setup: configure EDC/CDMS system; define user roles; set up integrations (labs, imaging, ePRO, vital signs etc.). 5. Vendor & external system contracts / specifications: lab vendors, imaging, safety databases, wearables etc. Define transfer, format, frequency, reconciliation. 6. System validation / testing / UAT (User Acceptance Testing): test the database, system workflows, edit checks, user acceptance, dummy data workflows; ensure compliance (e.g. audit trails, security, regulatory requirements like 21 CFR Part 11). 7. Training: site staff, data entry, monitors, vendor personnel, ensuring everyone understands CRFs, protocol, SOPs, data definitions. 8. Go-live: once everything is approved, the database goes live (data collection begins). | Sponsor, CRO (if outsourced), data management team, clinical operations, biostatistics, safety/pharmacovigilance, vendors (labs, imaging, etc.), quality assurance. | Finalized protocol; signed DMP; annotated CRFs/eCRFs; validated database; completed UAT; training logs; go-live approval. |
| II. Study Conduct & Ongoing Data Management | 1. Data capture / entry: site staff enter data via eCRF / other sources. 2. Real-time edit checks & validation: automated and manual checks to catch mismatches, missing data, logical inconsistencies. 3. Query / discrepancy management: generate queries, send to site, track resolution. 4. Source data verification (SDV) / Monitoring: onsite or remote monitoring, comparing source documents vs what is entered. 5. Safety data collection etc.: serious adverse events, adverse events, safety reporting, reconciliation between safety databases and eCRF / external systems. 6. Data integration from external systems: labs, imaging, ePRO, central labs, wearables etc.; ensure data format, units, reference ranges are handled properly. 7. Medical coding: adverse events, medications etc., using standard dictionaries (e.g. MedDRA, WHO-Drug). 8. Interim data cuts / analyses (if planned): extracting data snapshot, performing checks, feeding DSMB/IDMC etc. 9. Ongoing quality control & metrics: tracking query resolution times; site performance; data completeness; monitoring data entry timeliness; risk-based monitoring to focus effort where issues are greatest. | Data management team, site staff, monitors / CRAs, safety / pharmacovigilance, vendors, biostatistics (for interim), QA. | Regular data quality reports; updated query logs; safety reports; interim analysis deliverables; metrics dashboards. |
| III. Close-Out & Analysis Preparation | 1. Final data cleaning / reconciliation: ensure all queries closed; reconcile all external data (labs, imaging, safety, randomization / drug accountability systems). 2. Final QC reviews: ensure CRFs / eCRFs complete, protocol deviations documented, missing data handled, outliers checked. 3. Medical coding finalisation; ensure consistency; check that coding dictionaries versions are correct. 4. Database lock: after sponsor / data management / quality assurance sign-offs, database is locked (no further edits permitted) to prepare for final analysis. 5. Data export / dataset creation: analysis datasets created (e.g. CDISC SDTM / ADaM if applicable), tables/listings/figures (TLFs) prepared. 6. Regulatory / submission readiness: annotated CRFs, audit trails, all documentation (DMP, SOPs, system validation, query history). 7. Archiving: study data and documents archived (including eTMF / TMF), ensuring retention for required regulatory periods. 8. Final reporting & publications: Clinical Study Report (CSR), submission to regulatory authorities; manuscripts / presentations etc. | Data management, statistics / programming, QA / documentation, regulatory affairs, safety team. | Clean database; locked database; final datasets; CSR; submission package; archived documents; audit-ready TMF / eTMF. |