## 🧩 Database Lock Procedure in a Clinical Trial

### 1. Purpose

The purpose of the Database Lock (DBL) procedure is to ensure that the clinical database is accurate, complete, and verified before statistical analysis. Once locked, no changes can be made without formal approval and documentation.

### 2. Pre-Lock Activities

#### 2.1 Data Cleaning and Validation

- Data Management reviews all entered data for completeness and accuracy.

- Edit checks and data validation listings are run (e.g., missing values, out-of-range values, inconsistencies).

- Queries are raised and resolved by site personnel via EDC (Electronic Data Capture) system.

#### 2.2 Medical Coding

- Adverse Events (AEs) and Concomitant Medications (CMs) are coded using MedDRA and WHO Drug dictionaries respectively.

- Coding review is completed and reconciled.

#### 2.3 Serious Adverse Event (SAE) Reconciliation

- Clinical data and safety database (e.g., Argus, ArisG) are cross-checked to ensure all SAEs are consistent.

#### 2.4 External Data Reconciliation

- Central lab, ECG, imaging, and PK/PD data are reconciled with EDC data.

- All discrepancies are reviewed and resolved.

#### 2.5 Blinded Data Review Meeting (BDRM)

- Conducted before database lock while the study remains blinded.

- Participants: Clinical, Biostatistics, Data Management, Medical Monitor, Project Manager.

- Review inclusion/exclusion violations, protocol deviations, missing data, population flags (ITT, PP, Safety).

- Final decisions are documented and signed off.

#### 2.6 Data Validation Report

- Data Management generates a Data Validation Report summarizing the data cleaning status and confirming readiness for lock.

### 3. Lock Authorization

#### 3.1 Pre-Lock Checklist

A checklist is reviewed and signed off by responsible functions:

- All queries resolved

- All reconciliations complete

- All coding finalized

- SAE reconciliation complete

- Audit trail reviewed

- Approvals received from Data Management, Clinical, Biostatistics, and Project Management

#### 3.2 Lock Approval

- The Database Lock Authorization Form is circulated and approved (usually electronically).

- Approval is required from:

  - Data Management Lead

  - Biostatistics Lead

  - Clinical Lead

  - Project Manager / Sponsor Representative

### 4. Lock Execution

- Data Management executes the “Lock” function in the EDC system.

- User access is restricted — the database becomes read-only.

- A database snapshot (audit trail included) is archived for traceability.

### 5. Post-Lock Activities

#### 5.1 Database Transfer

- A final extract (SDTM/ADaM) is provided to Biostatistics for final analysis.

- Data transfer is validated and documented (checksum, date/time).

#### 5.2 Database Unlock (if needed)

- If errors are identified post-lock, a formal unlock procedure must be followed:

  - Justification documented.

  - Approval obtained from sponsor and QA.

  - Unlock and re-lock events logged in audit trail.

### 6. Documentation

- Data Validation Report

- Lock Authorization Form

- Lock Checklist

- Final EDC Export Log

- Audit Trail Report

- Database Lock Notification Email

### 7. Responsibilities

| Function | Responsibilities |
| --- | --- |
| Data Management (DM) | Leads data cleaning, validation, and executes database lock. |
| Biostatistics | Confirms data readiness, validates datasets, and performs final analysis post-lock. |
| Clinical Team | Reviews clinical data, protocol deviations, and approves readiness. |
| Project Management | Coordinates review timelines and ensures all functions complete pre-lock tasks. |
| Sponsor QA | May audit or review lock process documentation. |