A typical biostatistics budget in a CRO covers staff effort, software, meetings, and deliverables.

| Task / Deliverable | Resource | Estimated Hours | Rate ($/hour) | Total Cost ($) | Notes |
| --- | --- | --- | --- | --- | --- |
| Protocol Review & Sample Size Calculation | Senior Biostatistician | 20 | 100 | 2,000 | Includes discussions with Clinical Team |
| SAP Writing & Mock TLFs | Biostatistician | 40 | 80 | 3,200 | Primary and secondary analyses included |
| Programming (ADaM datasets) | Statistical Programmer | 60 | 60 | 3,600 | SDTM → ADaM derivations |
| Analysis & Tables/Figures | Biostatistician + Programmer | 50 | 80 / 60 | 3,800 | Primary, secondary, sensitivity analyses |
| QC / Validation | Independent Biostatistician | 20 | 90 | 1,800 | QC of all programs and outputs |
| Meetings / Client Communication | Manager | 10 | 120 | 1,200 | Kickoff, mid-study, final review |
| Total | - | 200 | - | 15,600 | - |

💡 Notes for CRO use:

- Break down by phase: Planning, Execution, Reporting.

- Include resource level: Junior / Senior / Manager.

- Add contingency (e.g., +10% hours) for unexpected deviations.