## 🕒 Biostatistician’s Role Timeline in a Clinical Trial

### 📘 Phase 0 — Concept & Feasibility (Months −12 to −9)

Goal: Define study objectives, endpoints, and feasibility.
Biostatistician’s Tasks:

- Advise on measurable and statistically sound endpoints.

- Estimate sample size ranges for budgeting and feasibility.

- Discuss possible estimands (treatment effects of interest).

- Contribute to protocol synopsis.

🧩 Output: Early statistical input summary.

### 🧭 Phase 1 — Protocol Design (Months −9 to −6)

Goal: Finalize protocol and statistical framework.
Tasks:

- Write the Statistical Methods section in the protocol.

- Finalize sample size calculation and assumptions.

- Define randomization method, analysis sets, and missing data strategies.

- Review CRF (Case Report Form) to ensure data supports planned analyses.

🧩 Output: Finalized protocol ready for IRB and regulatory submission.

### ⚙️ Phase 2 — Trial Setup (Months −6 to 0)

Goal: Prepare all systems and documents before first patient in (FPI).
Tasks:

- Develop Statistical Analysis Plan (SAP).

- Design randomization and stratification lists.

- Review data management plan and eCRF logic checks.

- Create mock tables, listings, and figures (TLFs).

- (Optional) Conduct simulation studies for power robustness.

🧩 Output: SAP, randomization files, mock shells.

### 💉 Phase 3 — Study Conduct (Month 0 to +12 or longer)

Goal: Support trial while it’s ongoing.
Tasks:

- Provide ongoing blinded data monitoring.

- Support interim analysis or Data Monitoring Committee (DMC) reports.

- Review protocol deviations and data quality metrics.

- Participate in blinded data review meeting (BDR) before unblinding.

🧩 Output: Interim and DMC statistical summaries, blinded data review results.

### 📊 Phase 4 — Database Lock & Analysis (Months +12 to +14)

Goal: Perform all planned analyses after data are finalized.
Tasks:

- Validate and lock analysis datasets (ADaM).

- Run primary and secondary analyses per SAP.

- Perform sensitivity and subgroup analyses.

- Prepare TLFs (Tables, Listings, Figures).

- Conduct QC/validation with an independent statistician/programmer.

🧩 Output: Final TLFs and statistical results package.

### 📄 Phase 5 — Reporting & Submission (Months +14 to +18)

Goal: Prepare materials for regulatory submission and publication.
Tasks:

- Write the Statistical Methods and Results sections of the CSR.

- Support regulatory queries (FDA/EMA).

- Contribute to publications and conference presentations.

- Archive analysis programs, outputs, and metadata.

🧩 Output: Clinical Study Report (CSR), submission-ready data package.

### 🌍 Phase 6 — Post-Trial / Lifecycle Support

Goal: Extend findings and support post-marketing needs.
Tasks:

- Conduct integrated analyses (pooled or meta-analyses).

- Design real-world evidence (RWE) or extension studies.

- Support label updates and safety monitoring.

🧩 Output: Post-marketing reports, manuscripts, RWE datasets.

Timeline chart (Gantt-style)

| Phase | Timeline | Biostatistician’s Main Focus |
| --- | --- | --- |
| Concept & Feasibility | −12 → −9 mo | Endpoint advice, initial sample size |
| Protocol Design | −9 → −6 mo | Protocol writing, estimand definition |
| Trial Setup | −6 → 0 mo | SAP, randomization, mock TLFs |
| Study Conduct | 0 → +12 mo | DMC support, data monitoring |
| Analysis & Lock | +12 → +14 mo | Final analysis, QC, tables |
| Reporting | +14 → +18 mo | CSR writing, regulatory responses |
| Post-Trial | +18+ mo | Meta-analysis, RWE, publications |

A high-level Gantt-style timeline showing when tasks happen:

| Task / Milestone | Start | End | Duration | Owner |
| --- | --- | --- | --- | --- |
| Project Kickoff Meeting | Jan 5 | Jan 5 | 1 day | Manager |
| Protocol Review | Jan 6 | Jan 20 | 2 weeks | Senior Biostatistician |
| Sample Size Calculation | Jan 6 | Jan 15 | 10 days | Senior Biostatistician |
| SAP Drafting | Jan 21 | Feb 10 | 3 weeks | Biostatistician |
| Mock TLFs | Feb 11 | Feb 20 | 1.5 weeks | Biostatistician |
| Programming ADaM Datasets | Feb 21 | Mar 10 | 3 weeks | Programmer |
| Analysis & TLF Generation | Mar 11 | Mar 31 | 3 weeks | Biostatistician + Programmer |
| QC / Validation | Apr 1 | Apr 10 | 1.5 weeks | Independent Biostatistician |
| CSR Writing | Apr 11 | Apr 25 | 2 weeks | Manager / Biostatistician |
| Final Deliverable Submission | Apr 26 | Apr 26 | 1 day | Manager |

💡 Tips for CRO project timelines:

- Show dependencies (e.g., SAP → ADaM programming → analysis).

- Track resource allocation to avoid overloading staff.

- Add milestones for client meetings and internal QC reviews.