# Project Plan: Safety and Efficacy of the Xanomeline Transdermal Therapeutic System (TTS) in Patients with Mild to Moderate Alzheimer’s Disease

## 1. Project Objectives

• Evaluate the efficacy of Xanomeline TTS in patients with mild to moderate Alzheimer’s disease using standardized scales such as ADAS-Cog, CIBIC+, and NPI.

• Assess safety by recording and analyzing adverse events (AEs/SAEs), vital signs, laboratory tests, and skin reactions.

• Investigate pharmacokinetics (PK) and tolerability to understand dose–response relationships.

• Standardize and prepare clinical data for FDA submission in CDISC SDTM and ADaM format.

## 2. Success Metrics

| Category | Target / Success Criteria |
| --- | --- |
| Efficacy | Primary endpoint (ADAS-Cog) improvement with p < 0.05 |
| Safety | No significant unexpected drug-related serious adverse events |
| Compliance | Completion rate ≥ 85% |
| Data Quality | Query rate < 5%; data error rate < 1% before data lock |
| Regulatory Compliance | No major findings in ICH-GCP and FDA inspections |
| Submission Quality | FDA eCTD submission passes validation |

## 3. Milestones and Deliverables

| Phase | Milestone | Deliverable |
| --- | --- | --- |
| Study Preparation | IND approval, site selection, investigator training | Protocol, IB, ICF, Site initiation package |
| Patient Enrollment & Treatment | Target enrollment completed | Enrollment logs, Treatment records |
| Interim Analysis | Blind interim analysis completed | Interim analysis report |
| Data Collection & Lock | Database locked | Final locked SDTM datasets |
| Statistical Analysis & CSR | Final analysis and report completed | TLFs, ADaM datasets, CSR |
| eCTD Submission | Submission to FDA completed | eCTD submission package |

## 4. Project Timeline (06 Jul 2012 – 05 Mar 2015)

| Phase | Task | Responsible Position | Start Date | End Date |
| --- | --- | --- | --- | --- |
| 1. Initiation & Preparation | Project initiation and budget approval | Project Manager | 06 Jul 2012 | 20 Jul 2012 |
|  | Protocol development and review | Medical Director / Biostatistician / Clinical Lead | 10 Jul 2012 | 30 Aug 2012 |
|  | Preparation of IB and ICF | Medical Writer / Regulatory Affairs | 01 Aug 2012 | 15 Sep 2012 |
|  | IRB/EC and IND submission | Regulatory Affairs Specialist | 10 Aug 2012 | 10 Oct 2012 |
|  | Site selection and contract execution | Clinical Operations / Legal | 01 Sep 2012 | 30 Oct 2012 |
|  | Investigator training and site initiation | CRA | 20 Oct 2012 | 15 Nov 2012 |
| 2. Enrollment & Treatment | Screening and randomization | Investigator / Site Staff | 15 Nov 2012 | 30 Jun 2013 |
|  | Treatment administration and monitoring | CRA / Site Staff | 01 Dec 2012 | 31 Mar 2014 |
|  | Safety reporting and drug accountability | Safety Officer / Pharmacovigilance | 01 Dec 2012 | 31 Mar 2014 |
| 3. Interim Analysis | Interim data cut | Data Management Lead | 01 Jul 2013 | 15 Jul 2013 |
|  | Blind interim analysis meeting | Biostatistician / Medical Monitor | 15 Jul 2013 | 15 Aug 2013 |
| 4. Data Collection & Lock | EDC review and query resolution | Data Management | 01 Apr 2013 | 30 Apr 2014 |
|  | Database lock | Data Management Lead / PM | 01 May 2014 | 15 May 2014 |
| 5. Statistical Analysis & Reporting | SAP development and approval | Biostatistician / PM | 15 Apr 2014 | 15 May 2014 |
|  | Primary and secondary endpoint analysis | Biostatistics Team | 16 May 2014 | 30 Jun 2014 |
|  | Safety analysis and integration | Safety Statistician | 01 Jun 2014 | 15 Jul 2014 |
|  | TLFs generation | Statistical Programmer | 15 Jun 2014 | 31 Jul 2014 |
|  | CSR drafting and review | Medical Writer / PM / Statistician | 01 Aug 2014 | 30 Sep 2014 |
| 6. Submission & Close-out | SDTM and ADaM dataset preparation | Statistical Programmer | 01 Jul 2014 | 31 Oct 2014 |
|  | eCTD clinical module preparation | Regulatory Submissions Team | 01 Oct 2014 | 15 Dec 2014 |
|  | Internal QA review | QA Lead / PM | 15 Dec 2014 | 15 Jan 2015 |
|  | FDA clinical submission (eCTD) | Regulatory Affairs | 01 Feb 2015 | 05 Mar 2015 |
|  | Project closure and lessons learned | Project Manager / Clinical Team | 01 Mar 2015 | 05 Mar 2015 |