## Slide 1: Project Timeline – Xanomeline TTS Clinical Trial
Full Lifecycle Overview (2012–2015)
Visual suggestion: Background image of Alzheimer’s care or molecular structure

## Slide 2: Study Design Summary
• Phase 3, randomized, double-blind, placebo-controlled
• Population: Mild to Moderate Alzheimer’s Disease
• Duration: 132 weeks (2012–2015)
Visual suggestion: Flowchart (Screening → Randomization → Treatment → Follow-up)

## Slide 3: Full Study Lifecycle (High-Level)
• Protocol Development → Study Startup → Enrollment → Analysis → CSR
• Clear milestones for tracking progress
Visual suggestion: Gantt-style timeline (2012–2015)

## Slide 4: Protocol Finalization & Approvals
• Draft completed: July 2012
• IRB/EC submission: Aug 2012
• Final approval: Oct 2012
Visual suggestion: Approval workflow diagram

## Slide 5: Study Startup (Q4 2012–Q2 2013)
• Site selection & initiation
• CRA & site staff training
• EDC build, UAT, and go-live
Visual suggestion: Milestone timeline chart

## Slide 6: Enrollment and Treatment (Jun 2013–Sep 2014)
• FPFV: June 2013
• Enrollment complete: Feb 2014
• LPLV: Sep 2014
Visual suggestion: Enrollment curve chart

## Slide 7: Data Management (2013–2014)
• CRF design & edit checks
• Query management & SAE reconciliation
• Interim data review
Visual suggestion: DM workflow diagram

## Slide 8: Statistical Programming & Analysis (Q4 2014–Q1 2015)
• DB Lock: Dec 2014
• TLF generation & QC
• ADaM & SDTM finalization
Visual suggestion: Overlapping tasks Gantt chart

## Slide 9: Clinical Study Report (CSR) Delivery (Mar 2015)
• Draft CSR: Feb 2015
• Sponsor QC & review
• Final submission: Mar 5, 2015
Visual suggestion: Document review workflow

## Slide 10: Interdepartmental Coordination
• DM–Stats–Medical Writing alignment
• Risk mitigation & version tracking
• Continuous feedback loops
Visual suggestion: Three-circle collaboration diagram

## Slide 11: Areas for Optimization
• Timeline compression opportunities
• EDC automation & real-time QC
• Improved cross-functional alignment
Visual suggestion: Current vs. Improved Timeline comparison

## Slide 12: What Can We Add or Improve?
• Review current timeline and propose enhancements
• Identify overlapping tasks to shorten the cycle
• Align on next steps this quarter
Visual suggestion: Simple lightbulb or arrow graphic